## Below 18m -7F (hidden)
Current High Risk Buildings/Projects
Proposed year | UPRN | Address | Postcode | Storeys | No. dwellings | Warranty | Rationale | Tenure | EWS required | comments
Expiration
21/22 | 9486 | 165 Iverson Road | NW6 2RB | 6 | 10 | 12/13/26 | Current high risk project - In litigation | SO | No | Under review with Freeholder
Managing agent - not Origin demise
| 8136 | Corsica St | N5 1FT | 4 | 25 |  | Known compartmentation and construction issues. | SO | Yes | Under review with developer
Metal cladding to upper floors and balconies
High risk building
Durkan construction
| 7941 | Fuller Court (1-9) | N8 8JD | 3 | 9 | 11/29/23 | Current high risk project in litigation with NHBC | SO | No
| 9909 | Fuller Court (28-56) |  | 5 | 11 |  |  | SO | Yes
Proposed schedule
Proposed year | UPRN | Address | Postcode | Storeys | No. dwellings | Warranty | Rationale | Tenure | EWS required | comments
Expiration
21/22 | 7187 | Spencer House, 156 Station Road | NW4 3AF | 3 | 8 | 2021-03-04 | Expiry date early 2021. timber cladding to exterior and metal spandrel panels. EWS1 completed 278/2/21 B1 | SO | No | Completed
| 6174 | 23 Parkway, Camden | NW1 7PG | 6 | 19 |  | ACM - carry over project from 2020 | L | Yes | PAS9980 completed. EWS1 B1
| 7793 | 185 Gt North Way (1-10) | NW4 1AU | 4 | 10 | 2023-01-02 | Known compartmentation and construction issues. HPL cladding to exterior. Metal cladding to upper floors. Durkan. | Rental | n/a
|  | (12-29) | NW4 1AU | 4 | 18 |  |  | SO | Yes
| 8538 | Essence Apartments (1-9) | HA3 7AF | 5 | 9 | 45569 | Known compartmentation issues (1-9) | L | No | Initial surveys completed by PRP (for MHCLG)
|  | (11-30) |  |  | 11 |  | Suspected timber frame construction. |  | No
Current high risk building - works not started
| 8241 | Bedstone | N18 1FE | 6 | 55 | 45933 | Large blocks. HPL. Suspected compartmentation issues. | Rent | No | Initial surveys completed by PRP (for MHCLG)
Would provide indications of rest of Watermill Lane
22/23 | 6209 | 3 Printers Avenue | WD18 | 3 | 10 |  | timber cladding EWI, supported housing |  | n/a | Supported
| 7823 | Kingsgate House | NW6 4TA | 4 | 38 | 2022-12-21 |  | SO | no | Developer 1 EWS1 A2 25/10/21
| 8064 | Attenborough Court 1-5 | WD19 4FN | 4 | 5 | 5/15/2022 | tile/timber cladding to upper floors. | R | n/a
| 8063 | Attenborough Court 6-24 | WD19 4FN | 4 | 9 |  |  | mixed | No
| 7016 | Narev Court | EN3 7JB | 4 | 8 |  | Panels on top floor (type unknown) timber base to balconies | SO | No
| 7824 | Westbourne House | NW6 4TB | 4 | 14 | 12/21/22 | EWI timber spandrels | R | n/a
23/24 | 7025 | Alder Court (12-59) | N11 2ND | 5 | 15 |  | Exterior cladding possibly ACM | SO | No | No responsibilities. Freeholder/MA
| 7824 | Wheelhouse Court (34-47) | N18 1ES | 4 | 14 | 2023-11-24 | Rainscreen metal cladding. HPL. EWI system. Potential compartmentation issues. | R | n/a | phase 1
| 7889 | Wheelhouse Court (1-11) |  | 3 | 11 | 2024-07-01 | Potential compartmentation issues | R | n/a | phase 1
| 7846 | Millpond Court (1-8,22,32-34) | N18 1ER | 4 | 34 | 2024-07-01 | Rain screen metal cladding. Suspected compartmentation. Watermill | R | n/a | phase 1
| 9916 | Millpond Court (9-21, 23-31) |  | 4
| 6153 | 537 Whippendell Rd | WD18 7QF | 4 | 9 |  | Timber cladding to walls and spandrel panels. Above commercial. | R | n/a
24/25 | 8499 | Wenlock House | EN1 1GU | 5 | 7 |  | weatherboard panels, EWI system. Timber bases to balconies | R | n/a
| 8240 | Penstock Court | N18 1ET | 4 | 33 | 3/22/25 | HPL. EWI system. Potential compartmentation issues. | R | n/a | phase 2
| 8441 | Runnersone Court | N18 1FF | 4 | 15 | 2025-07-06 | HPL. EWI system. Potential compartmentation issues. | so | Y | phase 3
| 8440 | Millrace Court | N18 1FD | 4 | 13 | 6/20/25 | HPL. EWI system. Potential compartmentation issues. | so | Y | phase 3
| 8439 | Undercroft Court | N18 1FB | 4 | 8 | 6/18/25 | HPL. EWI system. Potential compartmentation issues. | R | n/a | phase 3
25/26 | 6441 | St Ives Court | NW2 4HJ | 4 | 7 |  | Cladding to top floor (type unknown) | SO | Yes
| 8659 | Midlea House (1-14) | EN3 5NQ | 4 | 8 |  |  | ESH | n/a
| 9166 | Suffolk House | W1T 5JU | 5 | 11 |  | Top floor extension panelled sheet (unknown) | SO | Yes
| 7384 | 58C Vicarage Road | WD18 0GN | 3 | 10 |  | Same as Watson Court. Kier litigation. | R | n/a
| 7129 | Ball Court | NW9 5DX | 4 | 16 |  | EWS ? Spandrel panels unknown | R | n/a
| 6724 | Aubrey Lodge | EN2 8FL | 3 | 6 |  | external plastic cladding | SO | Y | Leaseholders and have no obligations. Freeholder/MA responsibility.
26/27 | 6084 | 83 Fleet Rd | NW3 2QY | 6 | 12 |  | Terracotta cladding/slips ? | R | n/a | Leaseholders and have no obligations. Freeholder/MA responsibility.
| 9315 | Lowry Court | HA3 5FD | 5 | 17 | 2028-01-28 | Survey undertaken 21/4/21 EWS1 B2 (remedials) | R | n/a
| 10914 | Ikon Apartments | N7 0FJ | 5 | 21 |  |  | mixed | Y
| 8170 | Staunton House | HA3 6JH | 3 | 7 |  | EWI system ?. Balconies timber decking and timber under canopies | R | n/a
| 9477 | Rhapsody Court | NW10 5DF | 3 | 7 |  |  | R | n/a | Leaseholders and have no obligations. Freeholder/MA responsibility.
27/28 | 9930 | Jacques house | HA3 6RD | 3 | 6 |  |  | R | n/a
| 4034 | Chandler House | NW6 7RD | 5 | 10 |  |  | R | n/a
| 6880 | Queensgate | WD17 2LQ | 6 | 28 | 6/30/20 | EWI system ?/brick slips | R | n/a | Leaseholders and have no obligations. Freeholder/MA responsibility.
|  | 159 Fellows Rd | done |  |  |  | survey undertaken 30/4/21. EWS1 B2 |  | Y | Completed
|  | 167 Fellows Rd | done |  |  |  | survey undertaken 30/4/21. EWS1 B2 |  | Y | Completed

## Below 18m -7F Revised
Current High Risk Buildings/Projects
Proposed year | UPRN | Address | Postcode | Storeys | No. dwellings | Warranty | Rationale | Tenure | EWS required | comments
Expiration
21/22 | 9486 | 165 Iverson Road | NW6 2RB | 6 | 10 | 12/13/26 | Current high risk project - In litigation | SO | No | Under review with Freeholder
Managing agent - not Origin demise
| 8136 | Corsica St | N5 1FT | 4 | 25 |  | Known compartmentation and construction issues. | SO | Yes | Under review with developer
Metal cladding to upper floors and balconies
High risk building
Durkan construction
| 7941 | Fuller Court (1-9) | N8 8JD | 3 | 9 | 11/29/23 | Current high risk project in litigation with NHBC | SO | No
| 9909 | Fuller Court (28-56) |  | 5 | 11 |  |  | SO | Yes
Proposed schedule
Proposed year | UPRN | Address | Postcode | Storeys | No. dwellings | Warranty | Rationale | Tenure | EWS required | comments
Expiration
21/22 | 7187 | Spencer House, 156 Station Road | NW4 3AF | 3 | 8 | 2021-03-04 | Expiry date early 2021. timber cladding to exterior and metal spandrel panels. EWS1 completed 278/2/21 B1 | SO | No | Completed
| 6174 | 23 Parkway, Camden | NW1 7PG | 6 | 19 |  | ACM - carry over project from 2020 | L | Yes | PAS9980 completed. EWS1 B1
| 7793 | 185 Gt North Way (1-10) | NW4 1AU | 4 | 10 | 2023-01-02 | Known compartmentation and construction issues. HPL cladding to exterior. Metal cladding to upper floors. Durkan. | Rental | n/a
|  | (12-29) | NW4 1AU | 4 | 18 |  |  | SO | Yes
| 8538 | Essence Apartments (1-9) | HA3 7AF | 5 | 9 | 45569 | Known compartmentation issues (1-9) | L | No | Initial surveys completed by PRP (for MHCLG)
|  | (11-30) |  |  | 11 |  | Suspected timber frame construction. |  | No | Further intrusive survey and PAS9980 review required.
Current high risk building - works not started
| 8241 | Bedstone | N18 1FE | 6 | 55 | 45933 | Large blocks. HPL. Suspected compartmentation issues. | Rent | No | Initial surveys completed by PRP (for MHCLG) Additional alarm installed > evacuate
[7 empty] | Would provide indications of rest of Watermill Lane |  |  | Further intrusive survey and PAS9980 review required.
22/23 | 7824 | Wheelhouse Court (34-47) | N18 1ES | 4 | 14 | 2023-11-24 | Rainscreen metal cladding. HPL. EWI system. Potential compartmentation issues. | R | n/a | phase 1
| 7889 | Wheelhouse Court (1-11) |  | 3 | 11 | 2024-07-01 | Potential compartmentation issues | R | n/a | phase 1
| 7846 | Millpond Court (1-8,22,32-34) | N18 1ER | 4 | 34 | 2024-07-01 | Rain screen metal cladding. Suspected compartmentation. Watermill | R | n/a | phase 1
| 9916 | Millpond Court (9-21, 23-31) |  | 4
| 6153 | 537 Whippendell Rd | WD18 7QF | 4 | 9 |  | Timber cladding to walls and spandrel panels. Above commercial. | R | n/a
23/24 | 8499 | Wenlock House | EN1 1GU | 5 | 7 |  | weatherboard panels, EWI system. Timber bases to balconies | R | n/a
| 8240 | Penstock Court | N18 1ET | 4 | 33 | 3/22/25 | HPL. EWI system. Potential compartmentation issues. | R | n/a | phase 2
| 8441 | Runnersone Court | N18 1FF | 4 | 15 | 2025-07-06 | HPL. EWI system. Potential compartmentation issues. | so | Y | phase 3
| 8440 | Millrace Court | N18 1FD | 4 | 13 | 6/20/25 | HPL. EWI system. Potential compartmentation issues. | so | Y | phase 3
| 8439 | Undercroft Court | N18 1FB | 4 | 8 | 6/18/25 | HPL. EWI system. Potential compartmentation issues. | R | n/a | phase 3
24/25 | 6441 | St Ives Court | NW2 4HJ | 4 | 7 |  | Cladding to top floor (type unknown) | SO | Yes
| 8659 | Midlea House (1-14) | EN3 5NQ | 4 | 8 |  |  | ESH | n/a
| 9166 | Suffolk House | W1T 5JU | 5 | 11 |  | Top floor extension panelled sheet (unknown) | SO | Yes
| 7384 | 58C Vicarage Road | WD18 0GN | 3 | 10 |  | Same as Watson Court. Kier litigation. | R | n/a
| 7129 | Ball Court | NW9 5DX | 4 | 16 |  | EWS ? Spandrel panels unknown | R | n/a
25/26 | 9315 | Lowry Court | HA3 5FD | 5 | 17 | 2028-01-28 | Survey undertaken 21/4/21 EWS1 B2 (remedials) | R | n/a
| 10914 | Ikon Apartments | N7 0FJ | 5 | 21 |  |  | mixed | Y
| 8170 | Staunton House | HA3 6JH | 3 | 7 |  | EWI system ?. Balconies timber decking and timber under canopies | R | n/a
| 9930 | Jacques house | HA3 6RD | 3 | 6 |  |  | R | n/a
| 4034 | Chandler House | NW6 7RD | 5 | 10 |  |  | R | n/a
|  | 159 Fellows Rd | done |  |  |  | survey undertaken 30/4/21. EWS1 B2 |  | Y | Completed
|  | 167 Fellows Rd | done |  |  |  | survey undertaken 30/4/21. EWS1 B2 |  | Y | Completed

## Buildings requiring safety case
BSF buildings
Proposed year | UPRN | Address | Postcode | Storeys | No. dwellings | Warranty | Rationale | P. Rating | Tenure | EWS required | comments
Expiration
21/22 (Y1) | 7395 | Watson Court | WD18 0FA | 8 | 144 | 2022-11-04 | Complex building. BSC being prepared by PRP | P1 .1 | Rent | No
| 3724 | Russell Mansions | WC1B 5AJ | 6 | 21 |  | Complex building. BSC being prepared by PRP | P3.5 | Mixed | No
| 4346 | Winifrede Paul | NW5 1DX | 7 | 18 |  | Vulnerable residents | P2.2 | Rent | No
22/23 (Y2) | 7890 | Wheelhouse Court | N18 1ES | 8 | 22 | 11/24/23 | HPL. EWI system. Potential compartmentation issues. | P1.1 | Rent | n/a
| 8169 | Archway Heights |  | 9 | 25 | 2022-04-10 | Currently in scaffold to remediate external façade. Unable to undertake safety case until remediation completed. EWS1 available after remediation and also priority rating reduced. In litigation with developer. | P1.1 | Rent | No | Deferred
| 9219 | Goldfinch Court | NW11 8AT | 7 | 31 | 3/15/25 | Remediation work in progress and unable to undertake safety case until remediation completed. EWS1 available after remediation and also priority rating also reduced. | P1.1 | Mixed | Yes | Deferred
| 8206 | 154 Loudon Road | NW8 0DJ | 8 | 33 | 11/22/24 | Will require remediation for parts of external structure. Scaffolding will be required. Unable to undertake safety case until remediation completed.EWS1 available after remediation and also priority rating reduced.Likely litigation with Durkan. | P1.1 | Lease | Yes | Deferred.
| 4607 | Robert Morton House | NW8 0DX | 7 | 46 |  | Care/retirement. Vulnerabilities | P2.2 | Rent | n/a
| 3336 | Hillwood House | NW1 1QH | 7 | 36 |  | Traditional construction | P3.5 | Rent | n/a
| 8512 | 37 Camden Road | NW1 9LR | 7 | 7 |  | Brick modern construction | P2.3 | SO | No | Freeholder responsibility.
23/24 (Y3)
| 2509 | St Richards House (1-18) | NW1 1BS | 7 | 18 |  | Traditional construction | P3.5 | Rent | n/a
| 7647 | St Richards House (19-38) | NW1 1BS | 7 | 20 |  | Traditional construction | P3.5 | Rent | n/a
| 7652 | St Richards House (41-59) | NW1 1BS | 7 | 17 |  | Traditional construction | P3.5 | Rent | n/a
| 2626 | Dulverton Mansions (1-15) | WC1X 8EJ | 7 | 15 |  | Traditional construction | P3.3 | Rent | n/a
| 7645 | Dulverton Mansions (16-29) | WC1X 8EJ | 7 | 14 |  | Traditional construction | P3.5 | Rent | n/a
| 7646 | Dulverton Mansions (30-50) | WC1X 8EJ | 8 | 20 |  | Traditional construction | P3.5 | Rent | n/a
24/25 (Y4) | 3486 | Barnstaple Mansions | EC1R 4SN | 7 | 13 |  | Traditional construction | P3.5 | Rent | n/a
| 3501 | Bideford Mansions | EC1R 4SJ | 7 | 12 |  | Traditional construction | P3.5 | Rent | n/a
| 3514 | Braunton Mansions | EC1T 4SY | 7 | 6 |  | Traditional construction | P3.5 | Rent | n/a
25/26(Y5) | 7105 | King Edward Court | HA9 7DQ | 11 | 14 |  | Octavia | P1.1 | Rent | n/a | Freeholder responsibility.
| 6732 | Mercury Court | NW1 1BR | 8 | 16 |  | Metal cladding panels and EWI | P1.1 | Rent | n/a | Freeholder responsible for external facade and structure. External survey identified issues with external façade. Freeholder seeking to claim against developer.
| 8330 | 175 Drummond Street | NW1 3FF | 10 | 68 | 2025-11-06 | Survey completed. EWS1 provide by British Land 25/3/20 Rating A3 | P1.5 | Rent |  | Survey completed. Determining if Freeholder is Principal Accountable Person
| 7248 | 2 Osnaburgh Street | NW1 3DF | 8 | 27 |  | Survey completed. EWS1 provide by British Land 26/6/20 Rating A2 | P1.5 | Rent |  | Survey completed. Determining if Freeholder is Principal Accountable Person
|  | 3 Longford Street | NW1 3NY | 8 | 24 |  | Survey completed. EWS1 provide by British Land 26/2/20 Rating A2 |  | Rent |  | Survey completed. Determining if Freeholder is Principal Accountable Person
|  | 8 Longford St | NW1 3BR | 8 | 35 |  | Survey completed. EWS1 provide by British Land 26/2/20 Rating A2 |  | Rent |  | Survey completed. Determining if Freeholder is Principal Accountable Person